## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-01-6f We bought a zoo
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Customer I want to search for a product so that I can find what i want to purchase quickly. | Given there is a product in the inventory when I input that product name then it should return the product object. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
| Given there is a product in the inventory when I input a product name that doesn't match a product then it should not return any products. |  |  | Pass
| Given there is no product in the inventory when I input a product name then it should not return a product object. |  |  | Pass
As a Customer I want to be able to add/remove products from the shopping cart so that I can buy checkout with all the products that I want to buy. | Given there is a product in the inventory when I add it to the shopping cart then the shopping cart should keep that item until it is removed. | Fail | AS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
| Given there is a product in the shopping cart when I remove it from the shopping cart then the shopping cart should keep that item until it is removed. |  |  | Pass
As a customer I want to be able to see my past purchase history so that I can keep track and look back at my orders | Given I purchase a product when I access my product history then I should see it in the list. | Fail | KL; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
As a customer I want to be able to change my address and phone number so that I can keep my account accurate to my information. | Given a user does not exist when I create a new user then I should be prompted to add personal information to the account. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
| Given a user exists when I input new personal information to be updated then the user should be updated to contain the new personal information. |  |  | Fail | KL; 4/1/2023; Users cannot change their information after being registered
As a customer, I want to create and keep track of my user name for the e-store website so that I can log as the same user. | Given a user exists when I log in with that username then it should log me in as that user. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
| Given a username does not exist when I log in with that username then it should create a new user and log me in as that user. |  |  | Pass
As an owner I want to easily be able to add new items on to the catalog so that it can be up to date with the on hand inventory. | Given a product is not in the inventory when I input a product object to be added then the product should be added to the inventory and be viewable on the catalog | Fail | AS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
As an owner I want to remove products from the catalog so that it can be up to date with the on hand inventory. | Given multiple of a product is in the inventory when I remove the product then the product's stock should decrease by one. | Fail | KL; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
As an owner I want to be able to edit products so that I can keep products up to date, change elements of it, and change the stock to correspond to my on hand inventory. | Given a product exists in the inventory when I input another product to update then it should change that product to match the new product. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. | Pass
As an owner I want to be able to view customer info such as name, email address, and contact information so that I can keep track of my users. | Given a user exists when I input the user ID then it should return the customer object associated with that user. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. |  | 4/1/2023 Not being implemented during this project
As an owner I want to be able to view customer billing information so that I can complete invoices for rentals. | Given a customer exists when I input a user ID then it should return the customer's billing information. | Fail | JS; 3/20/23; Backend for this worked but a bean error has popped up that we cant fix and therefore we cant run our application. |  | Team; 4/1/2023 Not being implemented during this project
As an owner I want to add and remove information so that I can keep the care information up to date. | Given a species exists when I input new information for that species then it should add a new information piece for that species. |  | 10% Feature, not worked on in this sprint
| Given a species does not exist when I input new information for that species then it will not add any information. |  | 10% Feature, not worked on in this sprint
| Given a piece of information exists when press remove on that information piece then it should remove that piece of information. |  | 10% Feature, not worked on in this sprint
As an owner I want to be able to update information so that I can make sure all information is accuate and am able to change it as I see fit | Given an information piece exists when I input an update to that information then the information should be replaced with what I input to update it. |  | 10% Feature, not worked on in this sprint
As a customer I want to be able to browse species information so that I can see how to take care of all species before I purchase one. | Given information exists when I log in as a user then I should be able to navigate to, and view all species care information. |  | 10% Feature, not worked on in this sprint
As a customer I want to receive information for the animals I have purchased so that I can quickly find information on the animals I have rented. | Given that I check out with my products, when I finalize my purchase, then I want to receive comprehensive information on how to care for those specific animals |  | 10% Feature, not worked on in this sprint